## Features
Type | Cost Driver | Possible Values | Parexel - Live Chat with DIY Integration Trigger | Decorah Bank - Bold360ai - 2 Bots (130 hrs @ $240) | Registrar/Bold360ai/Conversational Bot (3 Domains) | NA - Shelter Insurance, Bot with CSV, 80 hrs | SurePayroll/Bold360ai/Acquire Beta | Loews/Bold360ai/ServiceNow Bot Integration
| Submitted by |  | Aasim | Aasim | Aasim | Aasim | Aasim | Aasim
Customer & Use Case | Customer - Location | EMEA ¦India ¦ NA ¦ APAC | NA | NA | NA | NA | NA | NA
| Custom - Existing Bold Customer | Yes ¦ No | No | No | No | No | Yes | No
| Customer - Partner Involvement | Yes ¦ No | No | No | No | No | No | No
| Customer - Beauracratic | Yes ¦ No | No | No | No | No | No | No
| Customer Difficulty - Significant change requests | Yes ¦ No | Yes | No | No | No | No | No
| Custome Difficulty - Lacked skills to understand and maintain Bold | Yes ¦ No | No | No | No | Yes | No | No
| Customer Difficulty - Delays increasing PM overheads | Yes ¦ No | No | No | No | No | Yes | Yes
| Customer Difficulty - Required lots of meetings/engagements | Yes ¦ No | Yes | No | No | Yes | Yes | No
| Elaborate InfoSec Review during Project | Yes ¦ No | No | No | No | Yes | No | No
| Use case - End-Users | Internal ¦ External ¦ Both | Internal | External | External | Internal | External | Internal
| Use Case - Purpose | Sales ¦ Support ¦ Both | Support | Both | Both | Support | Both | Support
| Use Case - Rip & Replace | Yes ¦ No | No | No | No | No | No | No
| Product - Bold360ai | Yes ¦ No | Yes | Yes | Yes | Yes | No | Yes
| Product - Acquire | Yes ¦ No | No | No | No | No | Yes | No
| Product - Advise | Yes ¦ No | No | No | No | No | No | No
| Product - Bold360 Agent | Yes ¦ No | Yes | Yes | Yes | Yes | No | Yes
| Product - Rescue | Yes ¦ No | No | No | No | No | No | No
| Product Bugs - Impact on schedule | None ¦ Minor ¦ Significant | None | None | None | None | None | None
Front-End | Touchpoint - Support Center | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoint - Embedded Widget | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoints - AI Search Widget | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoints - AI Conversational Widget | # | 2 | 1 | 1 | 1 | 0 | 1
| Touchpoints - Agent Widget/Window | # | 2 | 1 | 1 | 1 | 0 | 1
| Touchpoints - Mobile App SDK Consulting | Yes ¦ No | No | No | No | No | No | No
| Touchpoint - Facebook | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoint - Whatsapp | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoint - WeChat | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoint - Teams | # | 0 | 0 | 0 | 0 | 0 | 0
| Touchpoint - Advise Chrome Extension | Yes ¦ No | No | No | No | No | No | No
| Touchpoint - Advise SFDC Widget | Yes ¦ No | No | No | No | No | No | No
| Support Center - 3-4 days for standard | None ¦ Standard ¦ Complex | None | None | None | None | None | None
| Front-end - Custom Widget Branding (Complex - >1 day) | None ¦ Simple ¦ Complex | Complex | Simple | Simple | Simple | Simple | Simple
| Front-end - Custom Workflows, Proactive, Forms, Channeling, Context (Complex - >1 day) | None ¦ Simple ¦ Complex | Complex | Simple | Complex | Complex | Complex | Complex
| Front-end - Analytics Integration | Yes ¦ No | No | No | No | No | No | No
| Front-end - Data masking | Yes ¦ No | No | No | No | No | No | No
| Front-end - Tag manager | Yes ¦ No | No | No | No | No | No | No
| Front-end - Accessibility | Yes ¦ No | No | No | No | No | No | No
| Conversion Tracking | Yes ¦ No | No | No | No | No | Yes | No
| Other peculiar asks | <text>
Integration | Connector - SNOW KB Sync | Yes ¦ No | No | No | No | No | No | Yes
| Connector - SFDC Connector for Agent | Yes ¦ No | No | No | No | No | No | No
| Connector - 3rd party live chat | Yes ¦ No | No | No | No | No | No | No
| Integration - DIY | Yes ¦ No | No | No | No | No | No | Yes
| Integration - Custom report, dashboard | Yes ¦ No | No | No | No | No | No | No
| Integration - Name of CRM or Ticketing tool | None ¦ SNOW ¦ Remedy ¦ Salesforce ¦ Inhouse ¦ Workato | None | None | None | None | None | SNOW
| Integration - Complex Node Providers (Multi-input or APIs, if-else logic, context mgmt) | # of Use Cases/ Articles | 0 | 0 | 0 | 0 | 0 | 3
| Integration - Simple Node Providers (Simple Retrieval, or Client-side only) | # of Use Cases/ Articles | 0 | 0 | 0 | 0 | 0 | 0
| Integration - Entities (CSV,JSON) | # of Use Cases/ Articles | 0 | 0 | 0 | 4 | 0 | 0
| Integration - Middleware Development | Yes ¦ No | No | No | No | No | No | No
| Integration - Consulting on API (Trigger) or Middleware | Yes ¦ No | No | No | No | No | No | No
| Integration - SSO | Yes ¦ No | Yes | No | No | Yes | No | No
| Integration - Rescue recording storage | Yes ¦ No | No | No | No | No | No | No
Content | KB - No. of Production KBs | # | 1 | 1 | 1 | 1 | 1 | 1
| KB - Primary Content Available (as opposed to building from scratch) | Yes ¦ No | No | No | No | No | Yes | Yes
| KB - Mass Content Import (CSV file) | None ¦ Straightforward ¦ Complex | Straightforward | Straightforward | Straightforward | Straightforward | None | Straightforward
| KB - Uses Context | Yes ¦ No | No | No | Yes | Yes | Yes | Yes
| Language - Geofluent | Yes ¦ No | No | No | No | No | No | No
| Language - Separate KBs | # | No | No | No | No | No | 0
Live Chat | No. of Live chat agents | # | 50 | 50 | 50 | 50 | 0 | 50
| Channel - Email | Yes ¦ No | No | Yes | Yes | No | No | No
| Channel - SMS | Yes ¦ No | No | No | No | No | No | No
| Channel - Facebook | Yes ¦ No | No | No | No | No | No | No
Output | Project - Duration (Months) | #
| Project - Budget | # | 60 | 130 | 100 | 80 | 30 | 185
| Project - Actual Hours Spent | # | 143 | 112.25 | 124.25 | 104 | 45.5 | 205.5
| Deduct from Hours - Onsite, Bugs, Others, Evy Involved? | #
| Add to Hours - CXM not logged hours | #
| Net Hours - IMPORTANT | # | 160 | 130 | 125 | 110 | 60 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QA by Evy | Yes ¦ No
| # Team Members | #
| Why did we go over - if we did? | CR ¦ Underscoped ¦ Underestimated ¦ Skill gaps ¦ Bugs ¦ Onsite | Underscoped ¦ Underestimated |  | CR ¦ Underscoped | Underscoped ¦ Underestimated | Underestimated ¦ Bugs ¦ Onsite | Underestimated