## Definitions of Complexity
Option | Definition | Examples/Use Cases | Typical Deployment Timeframe | Expiry | Requires API Documentation | Information Needed from Customer
Bold360ai Search Widget | Support Center or FAQ Widget |  | 4-6 Weeks | 90 days | No
Bold360ai Conversational Widget | Conversation Widget/Bot plus support centre |  | 6-8 Weeks | 120 days | No
Bold360 Chat Training | 2 online training sessions |  | 2 weeks | 30 days | No
Bold360 Quickstart | Simple live chat implementation with one chat journey and simple branding (icon, colours and fonts) |  | 4-6 Weeks | 60 days | No
Bold360 Express | Live chat implementation with up to 3 chat journeys and more sophisticated branding (custom CSS and/or js) |  | 6-12 Weeks | 90 days | No
Bold360 Tune-Up | Live chat implementation which includes 5 chat journeys, special branding and custom fields |  | 8-12 Weeks | 90 days | No
Bold360 Customer Care | Live chat implementation with one integration with back office system using API |  | n/a | 180 days | No
Bold360 Enterprise Chat | Live chat implementation with up to 3 integrations with back office system using API |  | n/a | 365 days | No
Bold360 Annual Strategy & Consulting | General good practise guidance and custom development for specific use cases |  | n/a | 120 days | No
Bold360 Pilot | 4 month pilot with up to 3 chat journeys, simple branding and specfic measurable targets Note: If pilot is the base package, there would be no additional add-ons |  | 4-6 weeks + monitoring | 120 days | No
What requires a NodeJS provider? | Dynamic data that is coming from an external system (not a predefined set of dynamic values (ex. Model numbers) If it requires an external REST API
Low Complexity NodeJS Provider | Single data point (field) Easily consumable REST API with no authentication | Store Locator (entering zip code to get resulting stores) | 2-4 Weeks |  | Yes | - API Docs - Bot workflow diagram for each use case
Medium Complexity NodeJS Provider | 1-3 data points (fields) Authenticated REST API Multiple end points | Order Status; Password Reset | 3-6 weeks |  | Yes | - API Docs - Bot workflow diagram for each use case
High Complexity NodeJS Provider | >3 data points (fields) Authenticated REST API Multiple end points | ServiceNow; Salesforce case creation | 4-8 weeks |  | Yes | - API Docs - Bot workflow diagram for each use case
What requires a CSV provider? | Static data set that can easily be hosted & managed in a google drive CSV file
Low Complexity CSV Custom Provider | Simple table (one column with unique values for indexing) Up to 100 rows of static data | Store opening times, services offering in store | 2-3 Weeks |  | No | - Bot workflow diagram for each use case - Content for CSV
Medium Complexity CSV Custom Provider | Multiple tables or multiple column indexing, non-unique values in columns | Same product name with multiple colors and sizes | 2-3 weeks
High Complexity CSV Custom Provider | >100 rows of static data | Store Locator (if all information resides in single CSV file) | 4-5 weeks |  | No | - Bot workflow diagram for each use case - Content for CSV
What requires a CRM integration? | If customer requires data to flow from the Bold system to an external system
Low Complexity CRM Integration (Agent) | API Triggers No Middleware required Customer supplied dev team to build endpoint | In-house CRM Basic authentication endpoint OR No authentication endpoint | 2-4 Weeks |  | Yes | - API Docs - Parmeters from the chat to be sent
High Complexity CRM integration (Agent) | Middleware Required Transform of data from Bold API trigger to customer endpoint Customer has not supplied has not supplied a dev team and CRM endpoint does not confrom to Bold360 API triggers | OAuth Requirement Incompatible endpoint for ingestion of CRM data | 4-6 Weeks |  | Yes | - API Docs - Parmeters from the chat to be sent
SDK Implentation (Native, iOS, Android) | Assistance with Android or iOS development app development (NOT mobile web) | Mobile app with chat bot functionality | n/a |  | No | Note: Any SDK implemtation is strictly consultative, the PS Team does not write any code or gain access to any Android or iOS applications
Additional Language Support | If not buying package with geofluent, then it will require replication of knowledge base in separate language for each language Requires a separate widget This is assuming customer will not be leveraging google analytics Per Language |  |  |  | No | Note: Conversational languages require confirmation with PS and CS that desired language is supported
KB Article Import | Manual import of articles Required when customer does not have method to export their existing knowledge base (KB) into our CSV template This can also happen when customers have image links that are broken from their content |  |  |  |  | - # of articles - Complexity of content (e.g. images, different versions based on context, charts, format of content, is it easily exportable) - Source of content"
Domains | How many separately deployed sites require a widget (# of URLs). Will the deployment for the two sites be handles differently (different code base)? Base package already assumes one. Only calculate extra domains if there are >1
Design | Design or any Front-End Customizations: Non-Standard Customization of Window: >10 hrs Standard is considered color changes, images, fonts, text changes Non-Standard: Custom javascript or CSS, image design Low Complexity: Medium: High:
Proactive Invitations | How many proactive invitations?

## Estimator
Options | Package/Scoping Item | Complexity | Count | Engineering Hours | PM Hours | Total Hours | Total Cost
Base Package
Base Package | Bold360 Conversational Widget | Simple |  | 46 | 28 | 74 | 22200
Add-On Packages
Add-On | + Agent | Simple | 1 | 3 | 3 | 6 | 1800
|  |  | 2 | 0 | 0 | 0 | 0
|  |  | 4 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
A La Carte - AI and Agent
Multi-Language
Geofluent Translation Service
Multiple KBs
Touchpoints
Mobile SDK
WhatsApp
WeChat
Facebook Messenger
MS Teams
A La Carte - AI
Entities
Simple
Medium
Complex
NodeJS Provider
Simple
Med
Complex
Channeling
Live Agent - External Vendor
Email - Ticketing
Advise Touchpoints
Chrome Extension
Salesforce Widget
A La Carte - Agent
Channels
SMS
FB Messenger
WhatsApp
WeChat
MS Teams
Email
Proactive Invitations
Simple
Med
Complex
DIY Integrations
Salesforce Connector
ZenDesk
Cusom
ServiceNow - KB Sync
Basic
Advanced Knowledge Plug-In
ServiceNow - Use Cases
Ticket Status
Leave a Comment
Cancel Ticket
Reopen Ticket
Check the Approval Status of RITM
Create an INC
Security Coordinator
Escalate
View Closed Tickets
Report an Issue
Custom
A la Carte Options - AI
Total
Note on E1: Alyssa Kafka: Development
Note on F1: Alyssa Kafka: Meetings, Trainings, Demos
Note on A63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Advanced Knowledge Widget?

## Inputs
Package/Scope Item | Complexity | Engineering Hours | PM Hours | Total Hours | Cost | Comments/Inputs | Questions 4/25
Low Complexity CRM Integration (Agent) |  | 13 | 3 | 16 | 4800 | Includes additional hour for training
Medium Complexity CRM integration (Agent) |  | 26 | 5 | 31 | 9300 | Includes additional hour for training
High Complexity CRM integration (Agent) |  | 26 | 5 | 31 | 9300 | Includes additional hour for training
Bold360 Conversational Widget | Simple | 46 | 28 | 74 | 22200
Bold360 Conversational Widget | Medium | 68 | 46 | 114 | 34200
Bold360 Conversational Widget | Complex | 102 | 80 | 182 | 54600
Bold360 Live Agent | Simple | 15 | 15 | 30 | 9000
Bold360 Live Agent | Medium | 28 | 22 | 50 | 15000
Bold360 Live Agent | Complex | 51 | 29 | 80 | 24000
Bold360 Support Center | Simple | 22 | 16 | 38 | 11400
+ Agent | Simple | 3 | 3 | 6 | 1800
+ Agent | Medium | 6 | 4 | 10 | 3000
+ Agent | Complex | 16 | 5 | 21 | 6300
+ Conversational Widget | Simple | 9 | 3 | 12 | 3600
+ Conversational Widget | Medium | 22 | 6 | 28 | 8400
+ Conversational Widget | Complex | 57 | 9 | 66 | 19800
+ Support Center | Simple | 10 | 1 | 11 | 3300
Low Complexity NodeJS Provider |  | 21 | 5 |  | 7800
Medium Complexity NodeJS Provider |  | 31 | 5 |  | 10800 | Includes 1 hour of additional training
High Complexity NodeJS Provider |  | 41 | 5 |  | 13800 | Includes 1 hour of additional training
Simple CSV Custom Provider |  | 11 | 10 |  | 6300 | Includes 1 hour of additional training
Complex CSV Custom Provider |  | 16 | 10 |  | 7800 | Includes 1 hour of additional training
SDK Implementation (Native, iOS, Android, Harmony) |  | 15 | 0 |  | 4500 |  | Do we need to change anything for the new harmony SDK?
Additional Language Support (Boldai Support Center) |  | 3 | 0 |  | 900 | Includes training
Additional Language Support (Boldai conversational) |  | 6 | 0 |  | 1800 | Includes training
Additional Language Support (Boldai Search) |  | 3 | 0 |  | 900 | Includes training
Geofluent |  | 9 | 1 |  | 3000
Chat Window Design - Low Complexity |  | 5 | 0 |  | 1500
Chat Window Design - Medium Complexity |  | 10 | 0 |  | 3000
Chat Window Design - High Complexity |  | 15 | 0 |  | 4500
Both
Multi-Language
Geofluent Translation Service |  | 9 | 1
# of hours for every additional language |  | 2
Multiple KBs
Touchpoints
Mobile SDK |  | 1 | 9
WhatsApp |  | 5 | 15
WeChat |  | 5 | 15
Facebook Messenger |  | 5 | 15
MS Teams |  | 5 | 15
AI A La Carte
Entities
Simple | Simple | 5
Medium | Medium | 15
Complex | Complex | 25
NodeJS Provider
Simple | Simple | 20
Med | Medium | 30
Complex | Complex | 40
Channeling
Live Agent - External Vendor |  | 2
Email - Ticketing |  | 2
Advise Touchpoints
Chrome Extension |  | 2 | 4
Salesforce Widget |  | 8 | 2
Context
| Count Based = per context variation | 2
Agent A La Carte
Channels
SMS
| Simple | 5
| Complex | 15
FB Messenger |  | 2
WhatsApp |  | 2
| Simple | 2
| Complex | 5 | 15
WeChat
| Simple | 2
| Complex | 5 | 15
MS Teams
| Simple | 2
| Complex | 5 | 15
Email
| Simple | 5
| Medium | 10
| Complex | 20
Proactive Invitations
Simple |  | 5
Med |  | 10
Complex |  | 15
Conversion Codes | Based on Count - per code | 10
DIY Integrations
Salesforce Connector |  | 10
ZenDesk |  | 5
Custom
| Simple | 10
| Medium | 20
| Complex | 40
ServiceNow - Instance
Simple | Simple
Medium | Medium
Complex | Complex
ServiceNow - KB Sync
Basic
Advanced Knowledge Plug-In
ServiceNow - Use Cases
Ticket Status
Leave a Comment
Cancel Ticket
Reopen Ticket
Check the Approval Status of RITM
Create an INC
Security Coordinator
Escalate
View Closed Tickets
Report an Issue
Custom
Note on A45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sessions with LionBridge to introduce geofluent and setup integration and troubleshoot initial setup
Note on A60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CSV
Note on A61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: JSON
Note on A62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: some combination
Note on A83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimates are based on using OOTB Twilio #s (Bold generated #s)
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OOTB Functionality
Note on B85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use of Auto Responder with various rules
Note on B88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add-On
Note on B89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stand alone
Note on B91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add-On
Note on B92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stand alone
Note on B94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add-On
Note on B95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stand alone
Note on A102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: <3
Note on A103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ~5
Note on A104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: >5
Note on A121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Advanced Knowledge Widget?

## Bot Only
Resource Name | Baseline | Simple Customer | Medium | Complex
Project Kick off & Planning Meeting | 4 | 4 | 4 | 4
Account Setup |  | 1 | 1 | 1
Requirements & Design Workshop | 4 | 4 | 6 | 8
Develop Detailed Project Plan | 2 | 2 | 3 | 5
Provide Content, Conversational and Reporting Training for Bold360ai | 8 | 3 | 4 | 8
Perform Functional Testing | 4 | 2 | 4 | 6
PM Admin Time | 4 | 4 | 8 | 16
Weekly Status |  | 8 | 16 | 32
PM | 26 | 28 | 46 | 80
Project Kick off & Planning Meeting | 4 | 4 | 4 | 4
Staging Site Setup |  | 1 | 1 | 1
Requirements & Design Workshop | 2 | 4 | 6 | 8
Window Design - Wireframes Conversational BOT | 3.2 | 0 | 0 | 0
Develop Detailed Project Plan | 2 | 1 | 2 | 3
Apply Standard customizations and Branding | 4 | 4 | 4 | 4
Phrasings | 2 | 0 | 0 | 0
Synonyms | 2 | 0 | 0 | 0
Bot Use cases | 2 | 0 | 0 | 0
Import Content | 4 | 1 | 1 | 1
Assist Customer with BOT usecase creation | 4 | 0 | 0 | 0
Review and implement suggested content (including Error messages, general answers, etc) | 4 | 4 | 4 | 4
Perform Functional Testing | 4 | 4 | 8 | 16
UAT Remediation | 12.8 | 8 | 16 | 26
Deploy Bold360 Bot Window | 2 | 2 | 2 | 2
Go Live Support | 2 | 2 | 3 | 4
Eng Admin Time | 4 | 2 | 4 | 8
Weekly Status |  | 4 | 8 | 16
Solution Design Documentation |  | 2 | 2 | 2 | Should bake in time for providers for documentation
Bot Configuration
Setup Channeling Policies (# and complexity) |  | 1 | 1 | 1
Feedback |  | 1 | 1 | 1
Labels |  | 1 | 1 | 1
ENG | 58 | 46 | 68 | 102
Total | 84 | 74 | 114 | 182
Add Ons
Context (Dependent on use case) - # of variations and complexity |  | 1 | 2 | 3
Front End Customizations |  | 5 | 10 | 15
SDK
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not done by an engineer. This would be for the CS Resource + Customer
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not done by an engineer. This would be for the CS Resource + Customer
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unsure what this is for
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Max 1 hour but this can be done by CS person or VIP
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't know what this is for
Note on A22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could include phraisngs and synonyms if needed.
Note on A33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need engineer's insight on if this varies based on project complexity

## Agent Base
| Quickstart | Express |  | Enterprise
Resource Name | Baseline | Simple Customer | Medium | Complex
Project Kick off & Planning Meeting | 0 | 1.5 | 2 | 2
Account Setup | 0 | 1 | 1 | 1
Requirements & Design Workshop | 0 | 0.5 | 1 | 2
Develop Detailed Project Plan | 0 | 1 | 2 | 3
Perform Functional Testing | 0 | 0 | 0 | 0
PM Admin Time | 0 | 4 | 6 | 8
Weekly Status |  | 4 | 6 | 8
Admin, Agent, Reporting Training | 4 | 3 | 4 | 5
PM | 0 | 15 | 22 | 29
Project Kick off & Planning Meeting | 1 | 1 | 1 | 1
Staging Site Setup |  | 1 | 1 | 1
Requirements & Design Workshop | 2 | 0.5 | 1 | 2
Develop Detailed Project Plan | 2 | 0.5 | 1 | 1
Apply Standard customizations and Branding | 0 | 1 | 4 | 8
Perform Functional Testing | 0 | 1 | 2 | 4
UAT Remediation | 0 | 1.5 | 3 | 6
Deploy Bold360 Window | 0 | 0.5 | 1 | 1
Go Live Support | 2 | 1 | 1 | 1
Eng Admin Time | 0 | 2 | 3 | 4
Weekly Status |  | 2 | 3 | 4
Solution Design Documentation |  | 1 | 2 | 3
Chat Window/ Button Configuration | 4 | 1 | 3 | 8
Departments/Agents/Websites |  | 0.5 | 1 | 4
Workflow Config |  | 0.5 | 1 | 3
ENG | 11 | 15 | 28 | 51
Total | 11 | 30 | 50 | 80
|  | 10500 |  | 20700
Conversion Codes
Proactive Invites
Routing Rules
Channels
SDK
AB Testing

## Support Center Base
Resource Name | Baseline | OOTB SC
Project Kick off & Planning Meeting | 2 | 2
Account Setup |  | 1
Requirements & Design Workshop | 2 | 2
Develop Detailed Project Plan | 1 | 1
Provide Content & Reporting Training | 2 | 2
Perform Functional Testing | 0 | 0
PM Admin Time | 4 | 4
Weekly Status |  | 4
PM | 11 | 16
Project Kick off & Planning Meeting | 2 | 2
Staging Site Setup | 2 | 1
Requirements & Design Workshop | 2 | 2
Develop Detailed Project Plan | 2 | 0
Apply Standard customizations and Branding | 4 | 2
Import Content | 1 | 1
Labeling Structure | 2 | 2
Perform Functional Testing | 2 | 1
UAT Remediation | 4 | 2
Deploy Support Center to Production | 2 | 2
Go Live Support | 2 | 2
Eng Admin Time | 4 | 2
Weekly Status |  | 2
Solution Design Documentation |  | 0
Setup Channeling Policies (# and complexity) |  | 0.5
Feedback |  | 0.5
ENG | 29 | 22
Total | 40 | 38
Add Ons
Custom Design
Standalone vs iFrame - what varies in complexity/hours?
|  | Simple | Medium | Complex
Admin, Agent, Reporting Training |  | 3 | 4 | 5
Live Agent Configuration
Chat Window/ Button Configuration |  | 1 | 3 | 8
Departments/Agents/Websites |  | 0.5 | 1 | 4
Workflow Config |  | 0.5 | 1 | 3
Solution Design Documentation |  | 1 | 1 | 1
Live Agent Add-On Total | 0 | 6 | 10 | 21
Requirements & Design Workshop |  | 1
Apply Standard customizations and Branding |  | 2
Staging Site Setup |  | 1
Import Content |  | 1
Labeling Structure |  | 2
Deploy Support Center to Production |  | 2
Setup Channeling Policies (# and complexity) |  | 0.5
Feedback |  | 0.5
Support Center Add On Total | 0 | 10

## Bot Base
Resource Name | Baseline | Simple Customer | Medium | Complex
Project Kick off & Planning Meeting | 4 | 4 | 4 | 4
Account Setup |  | 1 | 1 | 1
Requirements & Design Workshop | 4 | 4 | 6 | 8
Develop Detailed Project Plan | 2 | 2 | 3 | 5
Provide Content, Conversational and Reporting Training for Bold360ai | 8 | 3 | 4 | 8
Perform Functional Testing | 4 | 2 | 4 | 6
PM Admin Time | 4 | 4 | 8 | 16
Weekly Status |  | 8 | 16 | 32
PM | 26 | 28 | 46 | 80
Project Kick off & Planning Meeting | 4 | 4 | 4 | 4
Staging Site Setup |  | 1 | 1 | 1
Requirements & Design Workshop | 2 | 4 | 6 | 8
Window Design - Wireframes Conversational BOT | 3.2 | 0 | 0 | 0
Develop Detailed Project Plan | 2 | 1 | 2 | 3
Apply Standard customizations and Branding | 4 | 4 | 4 | 4
Phrasings | 2 | 0 | 0 | 0
Synonyms | 2 | 0 | 0 | 0
Bot Use cases | 2 | 0 | 0 | 0
Import Content | 4 | 1 | 1 | 1
Assist Customer with BOT usecase creation | 4 | 0 | 0 | 0
Review and implement suggested content (including Error messages, general answers, etc) | 4 | 4 | 4 | 4
Perform Functional Testing | 4 | 4 | 8 | 16
UAT Remediation | 12.8 | 8 | 16 | 26
Deploy Bold360 Bot Window | 2 | 2 | 2 | 2
Go Live Support | 2 | 2 | 3 | 4
Eng Admin Time | 4 | 2 | 4 | 8
Weekly Status |  | 4 | 8 | 16
Solution Design Documentation |  | 2 | 2 | 2
Bot Configuration
Setup Channeling Policies (# and complexity) |  | 1 | 1 | 1
Feedback |  | 1 | 1 | 1
Labels |  | 1 | 1 | 1
ENG Sub-Total | 62 | 46 | 68 | 102
Bot Total | 92 | 74 | 114 | 182
Admin, Agent, Reporting Training |  | 3 | 4 | 5
PM Sub-Total |  | 3 | 4 | 5
Live Agent Configuration
Chat Window/ Button Configuration |  | 1 | 3 | 8
Departments/Agents/Websites |  | 0.5 | 1 | 4
Workflow Config |  | 0.5 | 1 | 3
Solution Design Documentation |  | 1 | 1 | 1
ENG Sub-Total |  | 3 | 6 | 16
Live Agent Add-On Total | 0 | 6 | 10 | 21
Requirements & Design Workshop |  | 1
PM |  | 1 | 0 | 0
Requirements & Design Workshop |  | 1 | 0 | 0
Apply Standard customizations and Branding |  | 2
Staging Site Setup |  | 1
Import Content |  | 1
Labeling Structure |  | 2
Deploy Support Center to Production |  | 2
Setup Channeling Policies (# and complexity) |  | 0.5
Feedback |  | 0.5
ENG |  | 10 | 0 | 0
Support Center Add On Total | 0 | 11
|  | Same KB - Different Brand | Same KB - Different Experience | Completely Different Experience/BU
Requirements & Design Workshop |  | 1 | 2 | 3
Perform Functional Testing |  | 2 | 4 | 6
PM | 0 | 3 | 6 | 9
Staging Site Setup |  | 1 | 1 | 1
Requirements & Design Workshop |  | 0.5 | 1 | 2
Apply Standard customizations and Branding |  | 2 | 3 | 4
Import Content |  | 0 | 0.5 | 1
Review and implement suggested content (including Error messages, general answers, etc) |  | 0 | 1 | 2
Perform Functional Testing |  | 2 | 4 | 16
UAT Remediation |  | 1 | 8 | 26
Deploy Bold360 Bot Window |  | 0.5 | 0.5 | 1
Solution Design Documentation |  | 2 | 2 | 2
Bot Configuration
Setup Channeling Policies (# and complexity) |  | 0 | 1 | 1
Feedback |  | 0 | 0 | 1
ENG | 62 | 9 | 22 | 57
Bot Add On Total | 92 | 12 | 28 | 66
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not done by an engineer. This would be for the CS Resource + Customer
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not done by an engineer. This would be for the CS Resource + Customer
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unsure what this is for
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Max 1 hour but this can be done by CS person or VIP
Note on A22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't know what this is for
Note on A23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could include phraisngs and synonyms if needed.
Note on A34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need engineer's insight on if this varies based on project complexity
Note on A69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could include phraisngs and synonyms if needed.

## Revision History
# | Date Requested | Requested Revision | Status | Changes Made | Date Changed
1 | 2018-11-13 | Manual article import - # of minutes per article should be higher. Should re-estimate level of effort | Complete | Increased the minutes for the type of article to 30 minutes per article regardless of whether it's conversational or support center. | 2018-11-20
2 | 2018-11-13 | Additional Language Support - should vary for widget and escalation to agents, etc. Need these definitions and $/hours | Complete | Consider this the same amount of effort to create an entirely new bot so matched those numbers | 2018-11-20
3 | 2018-11-13 | Confirm training hours are incorporated in the PM allocation. Adjust as necessary | Complete | Baked in 1 hour to the additoinal integrations/providers for engineer to further train. Base packages already included those hours for training | 2018-11-20
4 | 2018-11-13 | Low Complexity CRM integration - underestimated? | Complete | Increased it per Manji's request | 2018-11-20
5 | 2018-11-20 | Incorporate Training Hours for SDK Implementation | Not Started | Pending inputs. Open question on who would be the one to deliver this training? PS team may not be qualified. Potentially needs to be product team to start and if requests increase, may need to train PS team
6 | 2019-04-25 | Changed base package options
7 | 2019-04-25 | Changed Language Cost and added Geofluent
8 | 2019-04-25 | Separated out training as its own item (Ai and Agent)
9 | 2019-04-25 | Added Client Side Providers
Testers: Mid-Market (Erica), Majors (TBD), International (TBD), CRM (TBD)