## Product Setup Schedule
Phase | Major Tasks (Starting 15-June) | Ownership | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Domain Research | Define Domain Experts | bar: 1 to 2
Finalize Features List | bar: 1 to 2
Finalize 100 sample projects | bar: 1 to 2
Data Collection | Collect inputs 1-on-1 | bar: 1 to 2
Get consensus on features
Modelling | Data Cleaning
Feature Engineering
Modelling
UAT | Define test group
Create feedback form
Fix issues found in feedback
Get consensus on deployment
Deployment | Build API endpoint
Build web app
Add monitoring systems | bar: 14 to 15
Wrap-up | Drive Adopton | bar: 16 to 17
Document | bar: 16 to 17
Project Closure
Legend
Planned
In Progress
Completed
Behind Schedule

## Resources
Roles | Name
Project Manager | Kashif
Developer | Jayendra
Data Scientist | Kashif
Domain Experts | Manji, Pablo